## Sheet1
End Date | Start Date | Status Date | Project | Project Manager | Project Category | Project Risk | Project Priority | Budget | Consumed Budget | Progress %
2020-09-01 | 2019-06-01 | 2019-06-01 | Digital Marketing Project | Gerardo Ferroni | Digital intelligence | Low | Medium | 1567357 | 25000 | 0
2020-09-01 | 2019-06-01 | 2019-07-01 | Digital Marketing Project | Gerardo Ferroni | Digital intelligence | Medium | Medium | 1567357 | 118017.3333 | 0.06
2020-09-01 | 2019-06-01 | 2019-08-01 | Digital Marketing Project | Gerardo Ferroni | Digital intelligence | Medium | Medium | 1567357 | 211034.6667 | 0.12
2020-09-01 | 2019-06-01 | 2019-09-01 | Digital Marketing Project | Gerardo Ferroni | Digital intelligence | Medium | Medium | 1567357 | 304052 | 0.18
2020-09-01 | 2019-06-01 | 2019-10-01 | Digital Marketing Project | Gerardo Ferroni | Digital intelligence | Medium | Medium | 1567357 | 397069.3333 | 0.24
2020-09-01 | 2019-06-01 | 2019-11-01 | Digital Marketing Project | Gerardo Ferroni | Digital intelligence | Medium | Medium | 1567357 | 490086.6667 | 0.3
2020-09-01 | 2019-06-01 | 2019-12-01 | Digital Marketing Project | Gerardo Ferroni | Digital intelligence | Medium | Medium | 1567357 | 583104 | 0.35
2020-09-01 | 2019-06-01 | 2020-01-01 | Digital Marketing Project | Gerardo Ferroni | Digital intelligence | High | Medium | 1567357 | 676121.3333 | 0.39
2020-09-01 | 2019-06-01 | 2020-02-01 | Digital Marketing Project | Gerardo Ferroni | Digital intelligence | High | Medium | 1567357 | 769138.6667 | 0.43
2020-09-01 | 2019-06-01 | 2020-03-01 | Digital Marketing Project | Gerardo Ferroni | Digital intelligence | High | Medium | 1567357 | 862156 | 0.47
2020-09-01 | 2019-06-01 | 2020-04-01 | Digital Marketing Project | Gerardo Ferroni | Digital intelligence | High | Medium | 1567357 | 955173.3333 | 0.51
2020-09-01 | 2019-06-01 | 2020-05-01 | Digital Marketing Project | Gerardo Ferroni | Digital intelligence | High | Medium | 1567357 | 1048190.6667 | 0.55
2020-09-01 | 2019-06-01 | 2020-06-01 | Digital Marketing Project | Gerardo Ferroni | Digital intelligence | High | Medium | 1567357 | 1141208 | 0.61
2020-09-01 | 2019-06-01 | 2020-07-01 | Digital Marketing Project | Gerardo Ferroni | Digital intelligence | High | Medium | 1567357 | 1234225.3333 | 0.67
2020-09-01 | 2019-06-01 | 2020-08-01 | Digital Marketing Project | Gerardo Ferroni | Digital intelligence | High | Medium | 1800000 | 1327242.6667 | 0.73
2020-09-01 | 2019-06-01 | 2020-09-01 | Digital Marketing Project | Gerardo Ferroni | Digital intelligence | High | Medium | 1800000 | 1420260 | 0.8
2020-09-01 | 2019-06-01 | 2020-10-01 | Digital Marketing Project | Gerardo Ferroni | Digital intelligence | High | Medium | 1800000 | 1568081.8016 | 0.9
2020-09-01 | 2019-06-01 | 2020-11-01 | Digital Marketing Project | Gerardo Ferroni | Digital intelligence | High | Medium | 1800000 | 1731289.0149 | 1
2021-08-31 | 2019-09-01 | 2019-09-01 | Supplier Management System | Sally Pujtkinski | Production & Quality | Low | High | 9009337 | 38000 | 0
2021-08-31 | 2019-09-01 | 2019-10-01 | Supplier Management System | Sally Pujtkinski | Production & Quality | Medium | High | 9009337 | 417939.8333 | 0.04
2021-08-31 | 2019-09-01 | 2019-11-01 | Supplier Management System | Sally Pujtkinski | Production & Quality | Low | High | 9009337 | 797879.6667 | 0.09
2021-08-31 | 2019-09-01 | 2019-12-01 | Supplier Management System | Sally Pujtkinski | Production & Quality | Low | High | 9009337 | 1177819.5 | 0.14
2021-08-31 | 2019-09-01 | 2020-01-01 | Supplier Management System | Sally Pujtkinski | Production & Quality | Low | High | 9009337 | 1557759.3333 | 0.18
2021-08-31 | 2019-09-01 | 2020-02-01 | Supplier Management System | Sally Pujtkinski | Production & Quality | Low | High | 9009337 | 1937699.1667 | 0.24
2021-08-31 | 2019-09-01 | 2020-03-01 | Supplier Management System | Sally Pujtkinski | Production & Quality | Low | High | 9009337 | 2317639 | 0.29
2021-08-31 | 2019-09-01 | 2020-04-01 | Supplier Management System | Sally Pujtkinski | Production & Quality | Low | High | 9009337 | 2697578.8333 | 0.33
2021-08-31 | 2019-09-01 | 2020-05-01 | Supplier Management System | Sally Pujtkinski | Production & Quality | Low | High | 9009337 | 3077518.6667 | 0.38
2021-08-31 | 2019-09-01 | 2020-06-01 | Supplier Management System | Sally Pujtkinski | Production & Quality | Low | High | 9009337 | 3457458.5 | 0.44
2021-08-31 | 2019-09-01 | 2020-07-01 | Supplier Management System | Sally Pujtkinski | Production & Quality | Low | High | 9009337 | 3837398.3333 | 0.49
2021-08-31 | 2019-09-01 | 2020-08-01 | Supplier Management System | Sally Pujtkinski | Production & Quality | Low | High | 9009337 | 4217338.1667 | 0.55
2021-08-31 | 2019-09-01 | 2020-09-01 | Supplier Management System | Sally Pujtkinski | Production & Quality | Low | High | 9009337 | 4597278 | 0.62
2021-08-31 | 2019-09-01 | 2020-10-01 | Supplier Management System | Sally Pujtkinski | Production & Quality | Low | High | 9009337 | 4751010.71 | 0.67
2021-08-31 | 2019-09-01 | 2020-11-01 | Supplier Management System | Sally Pujtkinski | Production & Quality | Low | High | 9009337 | 4874298 | 0.7
2021-08-31 | 2019-09-01 | 2020-12-01 | Supplier Management System | Sally Pujtkinski | Production & Quality | Low | High | 9009337 | 5044699.52 | 0.73
2021-08-31 | 2019-09-01 | 2021-01-01 | Supplier Management System | Sally Pujtkinski | Production & Quality | Low | High | 9009337 | 5444517.4529 | 0.76
2021-08-31 | 2019-09-01 | 2021-02-01 | Supplier Management System | Sally Pujtkinski | Production & Quality | Low | High | 9009337 | 5701447.98 | 0.81
2021-08-01 | 2019-09-02 | 2019-09-01 | Front-end tools Migration | Patrice Gattie | IT | Low | High | 2402844 | 24500 | 0
2021-08-01 | 2019-09-02 | 2019-10-01 | Front-end tools Migration | Patrice Gattie | IT | Medium | High | 2402844 | 152590.8599 | 0.04
2021-08-01 | 2019-09-02 | 2019-11-01 | Front-end tools Migration | Patrice Gattie | IT | Low | High | 2402844 | 280681.7199 | 0.08
2021-08-01 | 2019-09-02 | 2019-12-01 | Front-end tools Migration | Patrice Gattie | IT | Medium | High | 2402844 | 408772.5798 | 0.12
2021-08-01 | 2019-09-02 | 2020-01-01 | Front-end tools Migration | Patrice Gattie | IT | Medium | High | 2402844 | 536863.4397 | 0.16
2021-09-01 | 2019-09-02 | 2020-02-01 | Front-end tools Migration | Patrice Gattie | IT | Medium | High | 2402844 | 664954.2997 | 0.21
2021-09-01 | 2019-09-02 | 2020-03-01 | Front-end tools Migration | Patrice Gattie | IT | Medium | High | 2402844 | 793045.1596 | 0.24
2021-09-01 | 2019-09-02 | 2020-04-01 | Front-end tools Migration | Patrice Gattie | IT | High | High | 2402844 | 921136.0196 | 0.27
2021-09-01 | 2019-09-02 | 2020-05-01 | Front-end tools Migration | Patrice Gattie | IT | High | High | 2402844 | 1049226.8795 | 0.31
2021-09-01 | 2019-09-02 | 2020-06-01 | Front-end tools Migration | Patrice Gattie | IT | High | High | 2402844 | 1177317.7394 | 0.34
2021-09-01 | 2019-09-02 | 2020-07-01 | Front-end tools Migration | Patrice Gattie | IT | High | High | 2402844 | 1305408.5994 | 0.38
2021-09-01 | 2019-09-02 | 2020-08-01 | Front-end tools Migration | Patrice Gattie | IT | High | High | 2402844 | 1433499.4593 | 0.42
2021-09-01 | 2019-09-02 | 2020-09-01 | Front-end tools Migration | Patrice Gattie | IT | High | High | 2402844 | 1561590.3192 | 0.46
2021-09-01 | 2019-09-02 | 2020-10-01 | Front-end tools Migration | Patrice Gattie | IT | High | High | 2402844 | 1638772.8556 | 0.51
2021-09-01 | 2019-09-02 | 2020-11-01 | Front-end tools Migration | Patrice Gattie | IT | High | High | 2402844 | 1703256.6168 | 0.58
2021-09-01 | 2019-09-02 | 2020-12-01 | Front-end tools Migration | Patrice Gattie | IT | High | High | 2402844 | 1770277.7371 | 0.63
2021-10-01 | 2019-09-02 | 2021-01-01 | Front-end tools Migration | Patrice Gattie | IT | Medium | High | 2402844 | 1839936.0588 | 0.68
2021-10-01 | 2019-09-02 | 2021-02-01 | Front-end tools Migration | Patrice Gattie | IT | Medium | High | 2402844 | 1930876 | 0.78
2020-09-30 | 2019-12-01 | 2019-12-01 | Dématérialisation | Patrice Gattie | IT | Low | High | 2438787 | 0 | 0
2020-09-30 | 2019-12-01 | 2020-01-01 | Dématérialisation | Patrice Gattie | IT | Low | High | 2438787 | 250825.3164 | 0.1
2020-09-30 | 2019-12-01 | 2020-02-01 | Dématérialisation | Patrice Gattie | IT | Low | High | 2438787 | 501650.6329 | 0.22
2020-09-30 | 2019-12-01 | 2020-03-01 | Dématérialisation | Patrice Gattie | IT | Low | High | 2438787 | 752475.9493 | 0.32
2020-09-30 | 2019-12-01 | 2020-04-01 | Dématérialisation | Patrice Gattie | IT | Low | High | 2438787 | 1003301.2657 | 0.44
2020-09-30 | 2019-12-01 | 2020-05-01 | Dématérialisation | Patrice Gattie | IT | Low | High | 2438787 | 1254126.5822 | 0.55
2020-09-30 | 2019-12-01 | 2020-06-01 | Dématérialisation | Patrice Gattie | IT | Low | High | 2438787 | 1504951.8986 | 0.66
2020-09-30 | 2019-12-01 | 2020-07-01 | Dématérialisation | Patrice Gattie | IT | Medium | High | 2438787 | 1755777.215 | 0.75
2020-09-30 | 2019-12-01 | 2020-08-01 | Dématérialisation | Patrice Gattie | IT | Medium | High | 2500000 | 2006602.5315 | 0.85
2020-09-30 | 2019-12-01 | 2020-09-01 | Dématérialisation | Patrice Gattie | IT | High | High | 2500000 | 2257427.8479 | 0.95
2020-09-30 | 2019-12-01 | 2020-10-01 | Dématérialisation | Patrice Gattie | IT | High | High | 2500000 | 2535314 | 1
2021-01-03 | 2020-05-01 | 2020-05-01 | Pricing Intelligence | Gerardo Ferroni | Digital intelligence | Low | High | 3474722 | 10000 | 0
2021-01-03 | 2020-05-01 | 2020-06-01 | Pricing Intelligence | Gerardo Ferroni | Digital intelligence | Low | High | 3474722 | 671937.75 | 0.14
2021-01-03 | 2020-05-01 | 2020-07-01 | Pricing Intelligence | Gerardo Ferroni | Digital intelligence | Medium | High | 3474722 | 1333875.5 | 0.29
2021-01-03 | 2020-05-01 | 2020-08-01 | Pricing Intelligence | Gerardo Ferroni | Digital intelligence | Medium | High | 3474722 | 1995813.25 | 0.36
2021-01-03 | 2020-05-01 | 2020-09-01 | Pricing Intelligence | Gerardo Ferroni | Digital intelligence | Medium | High | 3474722 | 2657751 | 0.5
2021-01-03 | 2020-05-01 | 2020-10-01 | Pricing Intelligence | Gerardo Ferroni | Digital intelligence | Medium | High | 3474722 | 2883639 | 0.68
2021-01-03 | 2020-05-01 | 2020-11-01 | Pricing Intelligence | Gerardo Ferroni | Digital intelligence | Medium | High | 3474722 | 3064455 | 0.79
2021-01-03 | 2020-05-01 | 2020-12-01 | Pricing Intelligence | Gerardo Ferroni | Digital intelligence | Low | High | 3474722 | 3245271 | 0.9
2021-01-03 | 2020-05-01 | 2021-01-01 | Pricing Intelligence | Gerardo Ferroni | Digital intelligence | Low | High | 3474722 | 3426270.2778 | 1
2020-11-10 | 2020-05-01 | 2020-05-01 | Production - Scrap Management System | Gerardo Ferroni | Digital intelligence | Low | Medium | 705585 | 5200 | 0
2020-11-10 | 2020-05-01 | 2020-06-01 | Production - Scrap Management System | Gerardo Ferroni | Digital intelligence | Low | Medium | 705585 | 118137.6871 | 0.16
2020-11-10 | 2020-05-01 | 2020-07-01 | Production - Scrap Management System | Gerardo Ferroni | Digital intelligence | Medium | Medium | 705585 | 231075.3742 | 0.32
2020-11-10 | 2020-05-01 | 2020-08-01 | Production - Scrap Management System | Gerardo Ferroni | Digital intelligence | High | Medium | 705585 | 344013.0612 | 0.42
2020-11-10 | 2020-05-01 | 2020-09-01 | Production - Scrap Management System | Gerardo Ferroni | Digital intelligence | High | Medium | 705585 | 456950.7483 | 0.55
2020-11-10 | 2020-05-01 | 2020-10-01 | Production - Scrap Management System | Gerardo Ferroni | Digital intelligence | High | Medium | 705585 | 551292.3284 | 0.75
2020-11-10 | 2020-05-01 | 2020-11-01 | Production - Scrap Management System | Gerardo Ferroni | Digital intelligence | Medium | Medium | 705585 | 640607.4631 | 0.93
2020-11-10 | 2020-05-01 | 2020-12-01 | Production - Scrap Management System | Gerardo Ferroni | Digital intelligence | Medium | Medium | 705585 | 690553 | 1
2021-07-01 | 2020-07-01 | 2020-07-01 | HR Management Tool | Helen Allman | Human Resources | Low | Low | 426000 | 32000 | 0
2021-07-01 | 2020-07-01 | 2020-08-01 | HR Management Tool | Helen Allman | Human Resources | Medium | Low | 426000 | 101558.498 | 0.08
2021-07-01 | 2020-07-01 | 2020-09-01 | HR Management Tool | Helen Allman | Human Resources | Medium | Low | 426000 | 171116.996 | 0.16986
2021-07-01 | 2020-07-01 | 2020-10-01 | HR Management Tool | Helen Allman | Human Resources | Medium | Low | 426000 | 188513.4478 | 0.26575
2021-07-01 | 2020-07-01 | 2020-11-01 | HR Management Tool | Helen Allman | Human Resources | High | Low | 426000 | 203695.6187 | 0.34247
2021-07-01 | 2020-07-01 | 2020-12-01 | HR Management Tool | Helen Allman | Human Resources | Medium | Low | 426000 | 220100.505 | 0.41918
2021-07-01 | 2020-07-01 | 2021-01-01 | HR Management Tool | Helen Allman | Human Resources | Medium | Low | 426000 | 237826.5798 | 0.49589
2021-07-01 | 2020-07-01 | 2021-02-01 | HR Management Tool | Helen Allman | Human Resources | Low | Low | 426000 | 262005 | 0.59178
2021-02-01 | 2020-06-13 | 2020-07-01 | Identity and Access Management | Patrice Gattie | IT | Low | Low | 317545 | 25300 | 0
2021-02-01 | 2020-06-13 | 2020-08-01 | Identity and Access Management | Patrice Gattie | IT | Low | Low | 317545 | 75321 | 0.09
2021-02-01 | 2020-06-13 | 2020-09-01 | Identity and Access Management | Patrice Gattie | IT | Medium | Low | 317545 | 136332.0054 | 0.24
2021-02-01 | 2020-06-13 | 2020-10-01 | Identity and Access Management | Patrice Gattie | IT | Medium | Low | 317545 | 162915.0688 | 0.42
2021-02-01 | 2020-06-13 | 2020-11-01 | Identity and Access Management | Patrice Gattie | IT | Low | Low | 317545 | 187867.65 | 0.56
2021-02-01 | 2020-06-13 | 2020-12-01 | Identity and Access Management | Patrice Gattie | IT | Medium | Low | 317545 | 216642.0464 | 0.69
2021-02-01 | 2020-06-13 | 2021-01-01 | Identity and Access Management | Patrice Gattie | IT | Medium | Low | 317545 | 248008.0041 | 0.8
2021-02-01 | 2020-06-13 | 2021-02-01 | Identity and Access Management | Patrice Gattie | IT | Medium | Low | 317545 | 287482.1489 | 0.94
2021-03-02 | 2020-07-01 | 2020-07-01 | Records Management | Patrice Gattie | IT | Low | Medium | 657568 | 105000 | 0
2021-03-02 | 2020-07-01 | 2020-08-01 | Records Management | Patrice Gattie | IT | Low | Medium | 657568 | 132405 | 0.13
2021-03-02 | 2020-07-01 | 2020-09-01 | Records Management | Patrice Gattie | IT | Low | Medium | 657568 | 170000 | 0.3
2021-03-02 | 2020-07-01 | 2020-10-01 | Records Management | Patrice Gattie | IT | Low | Medium | 657568 | 271000 | 0.44
2021-03-02 | 2020-07-01 | 2020-11-01 | Records Management | Patrice Gattie | IT | Low | Medium | 657568 | 370000 | 0.54
2021-03-02 | 2020-07-01 | 2020-12-01 | Records Management | Patrice Gattie | IT | Low | Medium | 657568 | 449000 | 0.67
2021-03-02 | 2020-07-01 | 2021-01-01 | Records Management | Patrice Gattie | IT | Medium | Medium | 657568 | 518000 | 0.76
2021-03-02 | 2020-07-01 | 2021-02-01 | Records Management | Patrice Gattie | IT | Medium | Medium | 657568 | 597423 | 0.92
2021-08-30 | 2020-09-02 | 2020-09-01 | IT Program | Nathan Busterview | IT | Low | Medium | 1077104 | 124000 | 0
2021-08-30 | 2020-09-02 | 2020-10-01 | IT Program | Nathan Busterview | IT | Medium | Medium | 1077104 | 195031 | 0.09
2021-08-30 | 2020-09-02 | 2020-11-01 | IT Program | Nathan Busterview | IT | Medium | Medium | 1077104 | 280314 | 0.16
2021-08-30 | 2020-09-02 | 2020-12-01 | IT Program | Nathan Busterview | IT | High | Medium | 1077104 | 371923 | 0.24
2021-08-30 | 2020-09-02 | 2021-01-01 | IT Program | Nathan Busterview | IT | High | Medium | 1200000 | 451094 | 0.31
2021-08-30 | 2020-09-02 | 2021-02-01 | IT Program | Nathan Busterview | IT | High | Medium | 1200000 | 565430 | 0.38
2022-02-02 | 2020-09-02 | 2020-09-01 | Quality Evaluation Tool | Sally Pujtkinski | Production & Quality | Medium | Medium | 1849750 | 120000 | 0
2022-02-02 | 2020-09-02 | 2020-10-01 | Quality Evaluation Tool | Sally Pujtkinski | Production & Quality | Medium | Medium | 1849750 | 241573.8636 | 0.06
2022-02-02 | 2020-09-02 | 2020-11-01 | Quality Evaluation Tool | Sally Pujtkinski | Production & Quality | Medium | Medium | 1849750 | 338832.9545 | 0.13
2022-02-02 | 2020-09-02 | 2020-12-01 | Quality Evaluation Tool | Sally Pujtkinski | Production & Quality | Medium | Medium | 1849750 | 436092.0455 | 0.19
2022-02-02 | 2020-09-02 | 2021-01-01 | Quality Evaluation Tool | Sally Pujtkinski | Production & Quality | Medium | Medium | 1849750 | 533351.1364 | 0.23
2022-02-02 | 2020-09-02 | 2021-02-01 | Quality Evaluation Tool | Sally Pujtkinski | Production & Quality | Medium | Medium | 1849750 | 654925 | 0.3
2021-02-01 | 2020-08-15 | 2020-09-01 | Backup Evolution | Patrice Gattie | IT | Low | Low | 98000 | 0 | 0
2021-02-01 | 2020-08-15 | 2020-10-01 | Backup Evolution | Patrice Gattie | IT | Low | Low | 98000 | 33421 | 0.17
2021-02-01 | 2020-08-15 | 2020-11-01 | Backup Evolution | Patrice Gattie | IT | Medium | Low | 98000 | 48261 | 0.36
2021-02-01 | 2020-08-15 | 2020-12-01 | Backup Evolution | Patrice Gattie | IT | Medium | Low | 98000 | 63101 | 0.55
2021-02-01 | 2020-08-15 | 2021-01-01 | Backup Evolution | Patrice Gattie | IT | Medium | Low | 98000 | 77941 | 0.73
2021-02-01 | 2020-08-15 | 2021-02-01 | Backup Evolution | Patrice Gattie | IT | Medium | Low | 98000 | 96500 | 0.98
2021-06-02 | 2020-08-21 | 2020-09-01 | Unified Communication Project | Helen Allman | Human Resources | Low | Low | 454838 | 0 | 0
2021-06-02 | 2020-08-21 | 2020-10-01 | Unified Communication Project | Helen Allman | Human Resources | Low | Low | 454838 | 12597.2353 | 0.03
2021-06-02 | 2020-08-21 | 2020-11-01 | Unified Communication Project | Helen Allman | Human Resources | Medium | Low | 454838 | 62986.1765 | 0.12
2021-06-02 | 2020-08-21 | 2020-12-01 | Unified Communication Project | Helen Allman | Human Resources | Medium | Low | 454838 | 113375.1176 | 0.22
2021-06-02 | 2020-08-21 | 2021-01-01 | Unified Communication Project | Helen Allman | Human Resources | Medium | Low | 454838 | 163764.0588 | 0.34
2021-06-02 | 2020-08-21 | 2021-02-01 | Unified Communication Project | Helen Allman | Human Resources | Medium | Low | 454838 | 227591 | 0.5
2021-07-05 | 2020-09-01 | 2020-09-01 | Public cloud evolution | Nathan Busterview | IT | Low | Medium | 749000 | 0 | 0
2021-07-05 | 2020-09-01 | 2020-10-01 | Public cloud evolution | Nathan Busterview | IT | Low | Medium | 749000 | 85000 | 0
2021-07-05 | 2020-09-01 | 2020-11-01 | Public cloud evolution | Nathan Busterview | IT | Medium | Medium | 749000 | 141931.2 | 0.12
2021-07-05 | 2020-09-01 | 2020-12-01 | Public cloud evolution | Nathan Busterview | IT | Medium | Medium | 749000 | 198862.4 | 0.23
2021-07-05 | 2020-09-01 | 2021-01-01 | Public cloud evolution | Nathan Busterview | IT | Low | Medium | 650000 | 255793.6 | 0.35
2021-07-05 | 2020-09-01 | 2021-02-01 | Public cloud evolution | Nathan Busterview | IT | Low | Medium | 650000 | 326957.6 | 0.49
2021-11-01 | 2020-09-02 | 2020-09-01 | Finance Management System | Aileen Millimaki | Digital intelligence | Low | Low | 167111 | 21000 | 0
2021-11-01 | 2020-09-02 | 2020-10-01 | Finance Management System | Aileen Millimaki | Digital intelligence | Low | Low | 167111 | 24000 | 0.01
2021-11-01 | 2020-09-02 | 2020-11-01 | Finance Management System | Aileen Millimaki | Digital intelligence | Low | Low | 167111 | 29000 | 0.03
2021-11-01 | 2020-09-02 | 2020-12-01 | Finance Management System | Aileen Millimaki | Digital intelligence | Medium | Low | 167111 | 32000 | 0.07
2021-11-01 | 2020-09-02 | 2021-01-01 | Finance Management System | Aileen Millimaki | Digital intelligence | Medium | Low | 167111 | 36000 | 0.16
2021-11-01 | 2020-09-02 | 2021-02-01 | Finance Management System | Aileen Millimaki | Digital intelligence | Low | Low | 167111 | 40277.75 | 0.27
2021-08-24 | 2020-11-06 | 2020-11-01 | Finance Accounting | Aileen Millimaki | Digital intelligence | Medium | Medium | 665000 | 12000 | 0
2021-08-24 | 2020-11-06 | 2020-12-01 | Finance Accounting | Aileen Millimaki | Digital intelligence | Medium | Medium | 665000 | 34166.6667 | 0.03
2021-08-24 | 2020-11-06 | 2021-01-01 | Finance Accounting | Aileen Millimaki | Digital intelligence | Medium | Medium | 665000 | 122833.3333 | 0.13
2021-08-24 | 2020-11-06 | 2021-02-01 | Finance Accounting | Aileen Millimaki | Digital intelligence | High | Medium | 600000 | 233666.6667 | 0.26
2021-05-15 | 2020-08-16 | 2020-09-01 | BI & Pilotage | Aileen Millimaki | Digital intelligence | Low | Medium | 808400 | 218000 | 0.01
2021-05-15 | 2020-08-16 | 2020-10-01 | BI & Pilotage | Aileen Millimaki | Digital intelligence | Low | Medium | 808400 | 275000 | 0.06
2021-05-15 | 2020-08-16 | 2020-11-01 | BI & Pilotage | Aileen Millimaki | Digital intelligence | Low | Medium | 808400 | 301000 | 0.1
2021-05-15 | 2020-08-16 | 2020-12-01 | BI & Pilotage | Aileen Millimaki | Digital intelligence | Low | Medium | 808400 | 315000 | 0.15
2021-05-15 | 2020-08-16 | 2021-01-01 | BI & Pilotage | Aileen Millimaki | Digital intelligence | Medium | Medium | 808400 | 339000 | 0.19
2021-05-15 | 2020-08-16 | 2021-02-01 | BI & Pilotage | Aileen Millimaki | Digital intelligence | Medium | Medium | 808400 | 379000 | 0.27
2021-02-12 | 2020-08-14 | 2020-09-01 | LAN Field Evolution | Nathan Busterview | IT | Low | Low | 71500 | 12500 | 0.01
2021-02-12 | 2020-08-14 | 2020-10-01 | LAN Field Evolution | Nathan Busterview | IT | Low | Low | 71500 | 23000 | 0.12
2021-02-12 | 2020-08-14 | 2020-11-01 | LAN Field Evolution | Nathan Busterview | IT | Medium | Low | 71500 | 32000 | 0.24
2021-02-12 | 2020-08-14 | 2020-12-01 | LAN Field Evolution | Nathan Busterview | IT | Medium | Low | 71500 | 48000 | 0.32
2021-02-12 | 2020-08-14 | 2021-01-01 | LAN Field Evolution | Nathan Busterview | IT | High | Low | 71500 | 55000 | 0.47
2021-02-12 | 2020-08-14 | 2021-02-01 | LAN Field Evolution | Nathan Busterview | IT | High | Low | 82500 | 68000 | 0.65
2021-05-17 | 2020-11-27 | 2020-12-01 | Windows 10 Upgrade | Nathan Busterview | IT | Low | Low | 299900 | 28300 | 0.01
2021-05-17 | 2020-11-27 | 2021-01-01 | Windows 10 Upgrade | Nathan Busterview | IT | Low | Low | 299900 | 52000 | 0.08
2021-05-17 | 2020-11-27 | 2021-02-01 | Windows 10 Upgrade | Nathan Busterview | IT | Medium | Low | 299900 | 67000 | 0.14